## Sheet1
Requirement Number | SRS | Developer | Suspense Date | Completed | Phase 1 | Phase 2 | Phase 3 | On Time | Complete
1.1.0 | Web interface for user information | Kyle Deak | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-30 | 2017-08-06 |  | Yes
1.1.1 | Create HTML front end with userform | Kyle Deak | 2017-07-23 | 2017-07-22 | 2017-07-23 |  |  | Yes | Yes
1.1.2 | First Name textarea id=”firstname” | Kyle Deak | 2017-07-23 | 2017-07-22 | 2017-07-23 |  |  | Yes | Yes
1.1.3 | Last Name textarea id=”lastname” | Kyle Deak | 2017-07-23 | 2017-07-22 | 2017-07-23 |  |  | Yes | Yes
1.1.4 | Password textarea id=”whatever” | Kyle Deak | 2017-07-23 | 2017-07-22 | 2017-07-23 |  |  | Yes | Yes
1.1.5 | Confirm Password textarea id=”whatever2” | Kyle Deak | 2017-07-23 | 2017-07-22 | 2017-07-23 |  |  | Yes | Yes
1.1.6 | JavaScript validation method for password comparison | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
1.1.7 | Email textarea id=”email” | Kyle Deak | 2017-07-23 | 2017-07-22 | 2017-07-23 |  |  | Yes | Yes
1.1.8 | JavaScript email validation method | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
1.2.0 | MySQL table built to house username, password hash, email, first name, last name, last login date. Named User | John Delaney | 2017-07-23 | 2017-07-23 | 2017-07-23 |  |  | Yes | Yes
1.2.1 | Create MySQL table | John Delaney | 2017-07-23 | 2017-07-19 | 2017-07-23 |  |  | Yes | Yes
1.2.2 | Add Column First_Name VarChar 100 | John Delaney | 2017-07-23 | 2017-07-19 | 2017-07-23 |  |  | Yes | Yes
1.2.3 | Add Column Last_Name VarChar 100 | John Delaney | 2017-07-23 | 2017-07-19 | 2017-07-23 |  |  | Yes | Yes
1.2.4 | Add Column Username VarChar 100 | John Delaney | 2017-07-23 | 2017-07-19 | 2017-07-23 |  |  | Yes | Yes
1.2.5 | Add Column Email VarChar 150 | John Delaney | 2017-07-23 | 2017-07-19 | 2017-07-23 |  |  | Yes | Yes
1.2.6 | Add Column Password VarChar 512 | John Delaney | 2017-07-23 | 2017-07-19 | 2017-07-23 |  |  | Yes | Yes
1.2.7 | Add Column Last_Login Date | John Delaney | 2017-07-23 | 2017-07-19 | 2017-07-23 |  |  | Yes | Yes
1.2.8 | Add Column UserId VarChar 20 | John Delaney | 2017-07-23 | 2017-07-19 | 2017-07-23 |  |  | Yes | Yes
1.2.9 | Add Column Icon LONGBLOB | John Delaney | 2017-07-23 | 2017-07-19 | 2017-07-23 |  |  | Yes | Yes
1.3.0 | Php script to interact with web page and database to validate and place data in database. | John Delaney | 2017-07-30 |  | 2017-07-23 |  |  |  | No
1.3.1 | Php method for connecting to DB | John Delaney | 2017-07-23 | 2017-07-23 | 2017-07-23 |  |  | Yes | Yes
1.3.2 | Php method for data validation (size) | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
1.3.3 | Php method for posting to DB catch error/success and throw message back to Web | John Delaney | 2017-07-23 | 2017-07-23 | 2017-07-23 |  |  | Yes | Yes
1.3.4 | PHP method to add generic image to DB upon registration | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
1.4.0 | Web modal to catch returned information from a successful or unsuccessful registration. | Kyle Deak | 2017-08-06 |  |  |  | 2017-08-06 |  | No
Login Page
Requirement Number | SRS | Developer | Suspense
2.1.0 | Create User Login Page | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
2.1.1 | Create HTML with userform | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
2.1.2 | Username textarea id=”username” | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
2.1.3 | Password password field id=”pword” | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
2.1.4 | Create modal to catch login error to display | Kyle Deak | 2017-08-06 |  |  |  | 2017-08-06 |  | No
2.2 | Create PHP authenticate.php | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
2.2.1 | Create php method to select user info | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
2.2.2 | Create php method to compare credentials | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
2.2.3 | Create method to report bad login and pass message back to web. | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
2.2.4 | Create method to grant access to main application | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
Requirement Number | SRS | Developer | Suspense
3.1.0 | Create main GUI | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
3.1.1 | Build map using Leaflet.js place in <div> | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
3.1.2 | Build chat area textarea id=”message” | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
3.1.3 | Build chat submit button (works with enter as well) | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
3.1.4 | Build upload icon (avatar) select png, jpg, gif from local drive. | Kyle Deak | 2017-07-30 |  |  | 2017-07-30 |  |  | No
3.2.0 | Create Table in MySQL named Messages will house messages, latitude, longitude, and userid | John Delaney | 2017-07-23 | 2017-07-23 | 2017-07-23 |  |  | Yes | Yes
3.2.1 | Add Column UserId | John Delaney | 2017-07-23 | 2017-07-23 | 2017-07-23 |  |  | Yes | Yes
| Match UUID constraints | John Delaney | 2017-07-23 | 2017-07-23 | 2017-07-23 |  |  | Yes | Yes
3.2.2 | Add Column Messages VarChar 250 | John Delaney | 2017-07-23 | 2017-07-23 | 2017-07-23 |  |  | Yes | Yes
3.2.3 | Add Column Lat Numeric | John Delaney | 2017-07-23 | 2017-07-23 | 2017-07-23 |  |  | Yes | Yes
3.2.4 | Add Column Lon Numeric | John Delaney | 2017-07-23 | 2017-07-23 | 2017-07-23 |  |  | Yes | Yes
3.3.0 | Create PHP for main application chatGeo.php | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
3.3.1 | Create method to DB messages on submit | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
3.3.2 | Create method to Retrieve messages and coordinates | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
3.3.3 | Create method to DB image (avatar) | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
3.3.4 | Create method to retrieve new image | John Delaney | 2017-07-30 |  |  | 2017-07-30 |  |  | No
4. Server Side Security
Requirement Numer | SRS | Developer | Suspense
4.1.0 | All php calls to the DB will utilize best practices for secure transactions | John Delaney | 2017-08-06 |  |  |  | 2017-08-06 |  | No
[8 empty] | 48.08% | 48.08%